## Project Profile
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | PRJ_BankingExamPortal_001
Project Name | Banking Exam Portal Application
Prepared/Modified by | Role | Date of Preparation
Jitendra kushwah | Analyst | 26/12/2017
Reviewed by | Role | Date of Review
Manish kumar Nagle | Analyst | 26/12/17
Approved by | Role | Date of Approval
Dayanand Patil | Consultant | 26/12/17
Circulation List
Version Number | 1

## Defect Tracking Sheet
Project ID: | PRJ_BankingExamPortal_001 | Project Name : | Banking Exam Portal Application
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Defect Count | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_HOME_001 | Home | "List of Exams on the portal" link is failed to navigate the user to the web page displaying various exams available on the Banking Exam Portal application. | Detailed Description: | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | 26/01/2018 | Jitendra Kushwah |  | ACT |  | TC_EXAMREG_004
User is not able to navigate after clicking on "List of exams on the portal" link
Steps to reproduce bug:
1.Open browser
2.Enter URL for the website
3.Enter valid User Name
4.Enter valid Password
5.Click on Login Button
6.Click on "List of Exams on the portal"
Actual result observed on running above steps:
On executing the above mentioned steps it is observed that the application is not able to navigate the user to the web page. Link is not able to navigate to the page as expected.
DF_EXAMREG_002 | Banking Exam Portal | "List of Exams on the portal" link is found at the left side of the web page instead of right side. | Detailed Description: | Design | Google Chrome | Internal Dev | P3 | Low | 1.3.4 | 4 | 26/01/2018 | Jitendra Kushwah |  | ACT |  | TC_EXAMREG_005
List of Exams on the portal link is displayed at the left side of the web page
instead of right side.
DF_EXAMREG_003 | Banking Exam Registration | User name field is found to accept any type of data. | Detailed Description: | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | 26/01/2018 | Jitendra Kushwah |  | ACT |  | TC_EXAMREG_008
User is able to login succesfully even after entering special characters in the user name field.
Steps to reproduce bug:
1.Open browser
2.Enter URL for the website
3.Enter User Name
4.Enter valid Password
5.Click on Login Button
Actual result observed on running above steps:
On executing the above mentioned steps it is observed that the user can login successfully on the application.
DF_EXAMREG_004 | Banking_Exam_Registration | User is found to Login even if password field is left blank. | Detailed Description: | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | 26/01/2018 | Jitendra Kushwah |  | ACT |  | TC_EXAMREG_008
User has not entered password in the password field and clicks on login button, he can login successfully.
Steps to reproduce bug:
1.Open browser
2.Enter URL for the website
3.Enter User Name
4.Click on Login Button
Actual result observed on running above steps:
On executing the above mentioned steps it is observed that the User is able to login successfully even if the password field is left blank. There is no error message shown as expected.
DF_EXAMREG_005 | Home Page Validation | User is found to get error message “Page Cannot Be Displayed”, after clicking on the Submit button on the home page | Detailed Description: | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | 26/01/2018 | Jitendra Kushwah |  | ACT |  | TC_EXAMREG_009
User gets Error message "Page cannot be Displayed" after clicking on the home page.
Steps to reproduce bug:
1.Open browser
2.Enter URL for the website
3.Click on Submit button on the Home Page
Actual result observed on running above steps:
On executing the above mentioned steps it is observed that the User is getting an error message "Page cannot be displyed." after clicking on Submit button on Home Page.
DF_EXAMREG_006 | Login Validation | User is found to deny access to the Banking Exam Portal even he enters valid credentials. | Detailed Description: | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | 26/01/2018 | Jitendra Kushwah |  | ACT |  | TC_EXAMREG_008
User is not able to login to the Banking Exam Portal Application even if he enters valid User Name and valid Password.
Steps to reproduce bug:
1.Open browser
2.Enter URL for the website
3.Enter valid User Name
4.Enter valid Password
5.Click on Login Button
Actual result observed on running above steps:
On executing the above mentioned steps it is observed that the User is not able to login to the website.
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.

## Revision History
REVISION HISTORY OF WORK PRODUCT (to be maintained by projects)
# | Date | Version # | Section Changed | Details of changes made | Approved By